## Sheet1
Emp_Code |  | Emp_Name | Department
A3085 |  | Saurabh Raj Singh | ITSM
Date | Activity Planned for today | Task completed | Duration | Steps Taken | Pending Activity | Challeges faced
29/07/2021 | Join Forms,First Text Search,Indexing,Database Id,Regular Forms | Join Forms,First Text Search,Indexing | 3 hrs | Google | Database Id,Regular Forms | Not able to search exact definitions easily
30/07/2021 | Forms combination,Documents for Mid tier | Documents for Mid Tier | 4 | Google meeting,Google |  | Not able to search exact definitions easily
2021-02-08 | Form Joining | Pending | 3.5 | Google meeting,Google |  | Not able to search exact definitions easily
2021-03-08 | Default Fields,Palette | All | 3.5 | Google meeting,Google |  | Not able to search exact definitions easily
2021-04-08 | Result List,Application List,Keywords,Vendor form,View Form | All | 4.5 hr | Google meeting,Google |  | Practical Issue
2021-05-08 | Application Form,Result List,Application List,User form | All | 4.5 hr | Google meeting,Google |  | Practical Issue
2021-06-08 | Bundled Lisence,User Form,Deployable Application,Local Form | All | 4.5 hr | Google meeting,Google |  | Practical Issue
2021-09-08 | Lisecnse Types,Row Level Security,Menu | All | 4 hr | Google meeting,Google |  | Practical Issue
2021-10-08 | Lisecnse Types,Row Level Security,Menu | All | 4 hr | Google meeting,Google |  | Practical Issue
2021-11-08 | Menu,Lisecense Type,Case Study | All | 4 | Google meeting,Google |  | Practical Issue
2021-12-08 | Case Study | All | 4 | Google meeting,Google |  | Practical Issue
13/08/2021 | ARS Installation | Pending | 8 hr | Google meet |  | Error is displaying while Starting BMC Mid Tier
16/08/2021 | ARS Installation | Pending | 8 hr | Google meet |  | Error is displaying while Starting BMC Mid Tier
17/08/2021 | ARS Installation,Case Study | ARS Installation completed,Case Study Started | 8 hr | Google meeting,Google
18/08/2021 | Case Study | 0.3 | 8 hr | Google meeting,Google
19/08/2021 | Case Study | 0.4 | 8 hr | Google meeting,Google
20/08/2021 | Case Study | 0.6 | 8 hr | Google meeting,Google
21/08/2021 | Case Study | 0.6 | 8 hr | Self,Google |  | Error
23/08/2021 | Evaluation,Mock Test | All | 8 hr | Google meeting,Google |  | No
24/08/2021 | Demo User Exploration and ARS installation | All | 8 hr | Google meeting,Google |  | No
26/08/2021 | ARS Training+ Revision | All | 8 hr | Google meeting,Google |  | No
27/08/2021 | ARS Training+ Revision | All | 8 hr | Google meeting,Google |  | No
28/08/2021 | ARS Revision(Basic Test Preparation) | All | 8 hr | Google meeting,Google |  | No
30/08/2021 | ARS Revision+Basic Test+Advanced ARS Training | All | 8 hr | Google meeting,Google |  | No
31/08/2021 | ARS Training+ Revision | All | 8 hr | Google meeting,Google |  | No
2021-01-09 | ARS Training+ Revision | All | 8 hr | Google meeting,Google |  | No
2021-02-09 | ARS Training+ Revision | All | 8 hr | Google meeting,Google |  | No
2021-03-09 | ARS Training+ Revision | All | 8 hr | Google meeting,Google |  | No
2021-04-09 | Advanced ARS Study + ARS Retest Preparation | All | 8 hr | Google meeting,Google |  | No
2021-06-09 | Advanced ARS Study + ARS Retest | All | 8 hr | Google meeting,Google |  | No
2021-07-09 | ARS Assignment | All | 8 hr | Google meeting,Google |  | No
2021-08-09 | ARS Assignment+Evaluation | All | 8 hr | Google meeting,Google |  | No
2021-09-09 | ARS Assignment+Evaluation | All | 8 hr | Google meeting,Google |  | No
13/09/2021 | Advanded Case Study | 0.2 | 8 hr | Google meeting,Google |  | No
14/09/2021 | Advanded Case Study | 0.3 | 8 hr | Google meeting,Google |  | No
15/09/2021 | Advanded Case Study | 0.3 | 8 hr | Google meeting,Google |  | No
16/09/2021 | Advanded Case Study | 0.4 | 8 hr | Google meeting,Google |  | No
17/09/2021 | Advanded Case Study | 0.4 | 8 hr | Google meeting,Google |  | No
18/09/2021 | Advanded Case Study | 0.4 | 8 hr | Google meeting,Google |  | No
19/09/2021 | Advanded Case Study | 0.5 | 8 hr | Google meeting,Google |  | No
20/09/2021 | ITIL Training | 0.5 | 8 hr | Google meeting,Google |  | No
21/09/2021 | ITIL Training | 0.5 | 8 hr | Google meeting,Google |  | No
22/09/2021 | ARS Doubt Session + Advanded Case Study | All | 8 hr | Google meeting,Google |  | No
23/09/2021 | CS Session+ Advanced Case study | All | 8 hr | Google meeting,Google |  | No
24/09/2021 | CS Session+ Advanced Case study | All | 8 hr | Google meeting,Google |  | No
25/09/2021 | Advanded Case Study | 0.9 | 8 hr | Google meeting,Google |  | No
27/09/2021 | Advanded Case Study Work + Evaluation | All | 8 hr | Google meeting,Google |  | No
28/09/2021 | Advanded Case Study Work +Re- Evaluation | All | 8 hr | Google meeting,Google |  | No
29/09/2021 | ARS Final mock preparation | All | 8 hr | Google meeting,Google |  | No
30/09/2021 | ARS Final mock + Revision | All | 8 hr | Google meeting,Google |  | No
2021-01-10 | ARS Final Remock + Revision | All | 8 hr | Google meeting,Google |  | No
2021-04-10 | ITSM Installation+CS Session | 0.5 | 8 hr | Google meeting,Google |  | No
2021-05-10 | ITSM Installation+CS Session | All | 8 hr | Google meeting,Google |  | No
2021-06-10 | ITSM Installation+CS Session Assignment | All | 8 hr | Google meeting,Google |  | No
2021-07-10 | ITSM Installation+CS Session | All | 8 hr | Google meeting,Google |  | No
2021-08-10 | ITSM Training + CS Session+ITSM Revision | All | 8 hr | Google meeting,Google |  | No
2021-09-10 | ITSM Revision | All | 8 hr | Google meeting,Google |  | No
2021-11-10 | ITSM Revision | All | 8 hr | Google meeting,Google |  | No
2021-12-10 | ITSM Training+CS Session +Revision | All | 8 hr | Google meeting,Google |  | No
13/10/2021 | ITSM Revision+CS Session | All | 8 hr | Google meeting,Google |  | No
14/10/2021 | ITSM Training and Troubleshooting for UDM | All | 8 hr | Google meeting,Google |  | No
15/10/2021 | ITSM Training +Revision | All | 8 hr | Google meeting,Google |  | No
16/10/2021 | ITSM Training +Revision | All | 8 hr | Google meeting,Google |  | No
18/10/2021 | ITSM Training + CS Session+ITSM Revision | All | 8 hr | Google meeting,Google |  | No
19/10/2021 | ITSM Training + CS Session+ITSM Revision | All | 8 hr | Google meeting,Google |  | No
20/10/2021 | ITSM Training and Performance Review +CS Session+ITSM Revision | All | 8 hr | Google meeting,Google |  | No
21/10/2021 | ITSM Training +Revision | All | 8 hr | Google meeting,Google |  | No
22/10/2021 | ITSM Training +Revision+CS Session+Foundation and IM Assignment | All | 8 hr | Google meeting,Google |  | No
23/10/2021 | ITSM Revision+ Foundation and IM Assignment | All | 8 hr | Google meeting,Google |  | No
25/10/2021 | ITSM Training +Revision+CS Session + Foundation and IM Assignment Evaluation | All | 8 hr | Google meeting,Google |  | No
26/10/2021 | ITSM Training +Revision+CS Session | All | 8 hr | Google meeting,Google |  | No
27/10/2021 | ITSM Training +Revision+CS Session | All | 8 hr | Google meeting,Google |  | No
28/10/2021 | ITSM Training +Revision+CS Session | All | 8 hr | Google meeting,Google |  | No
29/10/2021 | ITSM Revision | All | 8 hr | Google |  | No
30/10/2021 | ITSM Revision | All | 8 hr | Google |  | No
2021-01-11 | ITSM Training +Revision | All | 8 hr | Google meeting,Google |  | No
2021-02-11 | ITSM Revision | All | 8 hr | Google |  | No
2021-08-11 | ITSM Revision | All | 8 hr | Google |  | No
2021-09-11 | SLM Installation | All | 8 hr | Google |  | No
2021-10-11 | SLM Installation and SLM Package Deployment | All | 8 hr | Google |  | No
2021-11-11 | SLM Assignment | All | 8 hr | Google |  | No
2021-12-11 | SLM Assignment and Evaluation | All | 8 hr | Google |  | No
13/11/2021 | SRM Installation | All | 8 hr | Google |  | No
14/11/2021 | SRM Installation | All | 8 hr | Google |  | No
15/11/2021 | SRM Installation and package Deployment | All | 8 hr | Google |  | No
16/11/2021 | SRM Installation and package Deployment | All | 8 hr | Google |  | No
17/11/2021 | ARS installation on Sonal machine | All | 8 hr | Google |  | No
18/11/2021 | ITSM installation on Sonal machine | All | 8 hr | Google |  | No
19/11/2021 | ITSM installation on Sonal machine | All | 8 hr | Google |  | No
20/11/2021 | ITSM installation on Aachal machine | All | 8 hr | Google |  | No
22/11/2021 | ITSM installation on Aachal machine | All | 8 hr | Google |  | No
23/11/2021 | ITSM installation on Aachal machine | All | 8 hr | Google |  | No
24/11/2021 | ITSM installation on Aachal machine | All | 8 hr | Google |  | No
25/11/2021 | ITSM installation on Aachal machine | All | 8 hr | Google |  | No
26/11/2021 | ITSM installation on Aachal machine and tried to solve issue regarding SRM | All | 8 hr | Google |  | No
27/11/2021 | ITSM installation on my machine due to issue caused regarding SRM | All | 8 hr | Google |  | No
29/11/2021 | SRM Training and Self leearning on SRM(Created company,SDT ,PDT, AOT) | All | 8 hr | Google,Google Meet |  | While setting the status as Request for Approval for SRD and saving it,it is set automatically as deployed
30/11/2021 | SRM Training and Self leearning on SRM(Created company,SDT ,PDT, AOT) | All | 8 hr | Google,Google Meet |  | We have made 3-4 SRD among which 1 is showing as pending
2021-01-11 | SRM Assignment | 0.2 | 8 hr | Google
2021-02-12 | SRM Assignment | 0.4 | 8 hr | Google
2021-03-12 | SRM Assignment and Evaluation | All | 8 hr | Google,Google Meet |  | We faced issues while raising the request as Incident ID is not getting generated.Also We faces while solving Nested PDT questions
2021-04-12 | Dummy Project SOW discussion,Nested PDT,SRM | 0.5 | 8 hr | Google,Google Meet |  | We faced issues in Nested PDT part
2021-06-12 | Dummy Project SOP duscussssion with Vaibhav and Rahul and ITSM Exploration | All | 8 hr | Google,Google Meet |  | Server Groups and Application Servers
2021-07-12 | Dummy Project SOP duscussssion with Vaibhav and Rahul and ITSM Exploration | All | 8 hr | Google,Google Meet
2021-08-12 | Dummy Project SOP duscussssion with Vaibhav and Rahul and Architecture and Pre-requisites,Asset Management Uninstallation | All | 8 hr | Google,Google Meet |  | Architecture and Pre Requisites
2021-09-12 | Explloration about BMC Remedy Compatibility Matrix and resharing of Architecture documents | All | 8 hr | Google,Google Meet |  | Java Patch and Microsoft IIS
2021-10-12 | Exploration about foundation data template,stand up meeting ans scrum call meeting | All | 8 hr | Google,Google Meet |  | Java Patch and Microsoft IIS
2021-11-12 | Exploration about foundation data template | All | 8 hr | Google,Google Meet |  | Java Patch and Microsoft IIS
13/12/2021 | Prepared Roadmap for Foundation data upload and trouble shooting error for UDM | All | 8 hr | Google,Google Meet |  | Roadmap for foundation data upload
14/12/2021 | Prepared Roadmap for Foundation data upload and Question-Answers and troubleshooting error for UDM | All | 8 hr | Google,Google Meet |  | Questions and Answers related to UDM,Foundation data Mapping
15/12/2021 | Foudation Data Implementation | All | 8 hr | Google,Google Meet
16/12/2021 | Foundation Data Upload(Company,organization,Support Group),Fixed Issues related to Uploading Foundation data | All | 8 hr | Google,Google Meet |  | Facing Issue related to Foundation Data
17/12/2021 | Foundation Data Upload(Company,organization,Support Group,Operational Categories),Fixed Issues related to Uploading Foundation data | All | 8 hr | Google,Google Meet |  | Facing Issue related to Foundation Data
18/12/2021 | Foundation Data Upload(Product and Operational Categories) | All | 8 hr | Google,Google Meet |  | Facing Issue related to Foundation Data
20/12/2021 | Client Meeting,Foundation Data deletion and Modification in Foundation data as descussed by Rahul over the call | All | 8 hr | Google,Google Meet |  | Facing Issue related to Foundation Data
21/12/2021 | Client Meeting,Foundation Data Update and explored ARS Basics | All | 8 hr | Google,Google Meet |  | Facing Issue related to Foundation Data
22/12/2021 | Client Meeting,Worked on Raising Incident through SRD and Incident Management Console | All | 8 hr | Google,Google Meet |  | Facing Issue related to Foundation Data
23/12/2021 | Client Meeting,WorkedRequirements given by client | All | 8 hr | Google,Google Meet |  | Facing Issue related to Foundation Data
24/12/2021 | Worked on client requirement and Reloaded support group data | All | 8 hr | Google,Google Meet |  | Facing Issue related to Foundation Data
27/12/2021 | Foundation Data Modification in Location data and Worked on client requirement | All | 8 hr | Google,Google Meet |  | Facing Issue related to Foundation Data
28/12/2021 | Worked on Client Requirements | All | 8 hr | Google,Google Meet |  | Facing Issue related to Client Requirement
29/12/2021 | Worked on Client Requirements | All | 8 hr | Google,Google Meet |  | Facing Issue related to Client Requirement
30/12/2021 | Worked on Client Requirements | All | 8 hr | Google,Google Meet |  | Facing Issue related to Client Requirement
31/12/2021 | Worked on Client Requirements | All | 8 hr | Google,Google Meet |  | Facing Issue related to Client Requirement
2022-03-01 | Worked on Client Requirements(Assignemtn Configuration for Incident and change module) | All | 8 hr | Google,Google Meet |  | Facing Issue related to Client Requirement
2022-04-01 | Worked on client requirements,Requirements Demo | All | 8 hr | Google,Google Meet |  | Facing Issue related to Client Requirement
2022-05-01 | Worked on client requirements,Email Configuration | All | 8 hr | Google,Google Meet |  | Facing Issue related to Client Requirement
2022-06-01 | Worked on the Client Requirements,Email Configuration,Prepared Documents | All | 8 hr | Google,Google Meet |  | Facing Issue related to Client Requirement